## P
UniqueID | Sr. No | Product Name | Order Processing Date | Promised Delivery Date | Quantity Required | Components | Operation | Process Type | Machine Number | Run Time (min/1000) | Cycle Time (seconds) | Setup time (seconds) | Ready Time | Start Time | End Time | Wait Time | Status | Time Diff | SetupTimeCheck
1 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C1 | Op1 | In House | M1 | 10 | 1.08 | 10000 | 45435.375 |  |  | 0:00 |  | 0
2 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C2 | Op2 | Outsource | OutSrc | 1440 |  | 10000 | 45435.375 |  |  | 0:00 |  | 0
3 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C3 | Op3 | In House | M2 | 20 | 7.2 | 10000 | 45435.375 |  |  | 0:00 |  | 0
4 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C4 | Op4 | In House | M1 | 30 | 1.08 | 10000 | 45435.375 |  |  | 0:00 |  | 0
5 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C5 | Op5 | In House | M3 | 15 | 7.2 | 10000 | 45435.375 |  |  | 0:00 |  | 0
6 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C6 | Op5 | In House | M3 | 14 | 7.2 | 10000 | 45435.375 |  |  | 0:00 |  | 0
7 | 2 | Product 2 | 2024-08-19 | 2024-08-27 | 4000 | C1 | Op1 | In House | M1 | 30 | 3 | 0 | 45435.375 |  |  | 0:00 |  | 0
8 | 2 | Product 2 | 2024-08-19 | 2024-08-27 | 4000 | C2 | Op2 | In House | M2 | 30 | 7.2 | 10000 | 45435.375 |  |  | 0:00 |  | 0
9 | 2 | Product 2 | 2024-08-19 | 2024-08-27 | 4000 | C3 | Op3 | Outsource | OutSrc | 700 |  | 0 | 45435.375 |  |  | 0:00 |  | 0
10 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C1 | Op1 | Outsource | OutSrc | 1440 |  | 10000 | 45435.375 |  |  | 0:00 |  | 0
11 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C2 | Op2 | In House | M1 | 30 | 1.08 | 10000 | 45435.375 |  |  | 0:00 |  | 0
12 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C3 | Op3 | In House | M2 | 40 | 7.2 | 10000 | 45435.375 |  |  | 0:00 |  | 0
13 | 4 | Product 4 | 2024-08-21 | 2024-08-29 | 5000 | C1 | Op1 | Outsource | OutSrc | 750 | 1.08 | 10000 | 45435.375 |  |  | 0:00 |  | 0
14 | 4 | Product 4 | 2024-08-21 | 2024-08-29 | 5000 | C2 | Op2 | In House | M1 | 35 |  | 10000 | 45435.375 |  |  | 0:00 |  | 0
15 | 4 | Product 4 | 2024-08-21 | 2024-08-29 | 5000 | C3 | Op3 | In House | M2 | 30 | 7.2 | 10000 | 45435.375 |  |  | 0:00 |  | 0
16 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C1 | Op1 | In House | M1 | 40 | 1.08 | 10000 | 45435.375 |  |  | 0:00 |  | 0
17 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C2 | Op2 | In House | M2 | 40 | 7.2 | 10000 | 45435.375 |  |  | 0:00 |  | 0
18 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C3 | Op3 | In House | M2 | 35 | 7.2 | 10000 | 45435.375 |  |  | 0:00 |  | 0
20 | 6 | Product 6 | 2024-08-21 | 2024-08-19 | 4000 | C1 | Op1 | In House | M1 | 30 | 7.2 | 10000 | 45435.375 |  |  | 0:00 |  | 0
21 | 6 | Product 6 | 2024-08-21 | 2024-08-19 | 4000 | C2 | Op2 | In House | M2 | 30 |  | 10000 | 45435.375 |  |  | 0:00 |  | 0
22 | 6 | Product 6 | 2024-08-21 | 2024-08-19 | 4000 | C3 | Op3 | In House | M3 | 30 | 1.08 | 10000 | 45435.375 |  |  | 0:00 |  | 0

## prodet
UniqueID | Sr. No | Product Name | Order Processing Date | Promised Delivery Date | Quantity Required | Components | Operation | Process Type | Machine Number | Run Time (min/1000) | Cycle Time (seconds) | Setup time (seconds) | Ready Time | Start Time | End Time | Wait Time | Status | Time Diff | SetupTimeCheck | Remaining_days | Time_Needed | Run_time | Final Setup Time | Delay Days | Delay Hours | Time Diff_days | Idle Time
1 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C1 | Op1 | In House | M1 | 10 | 1.08 | 10000 | 2024-05-23 09:00 | 2024-08-19 15:02 | 2024-08-19 16:32 | 06:01:30 | Completed | 01:30:00 | 0 | -9 | -4320 | 90 | 10000 | 0 | 0 | 0.0625 | 07:30:00
2 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C2 | Op2 | Outsource | OutSrc | 1440 |  | 10000 | 2024-05-23 09:00 | 2024-08-19 16:32 | 2024-08-22 16:32 |  | Completed | 00:00:00 | 1 | -9 | -4320 | 1440 |  |  |  | 3 | 09:00:00
3 | 1 | Product 1 | 2024-08-21 | 2024-08-28 | 9000 | C3 | Op3 | In House | M2 | 20 | 7.2 | 10000 | 2024-05-23 09:00 | 2024-08-22 16:32 | 2024-08-23 11:33 | 07:32:30 | Completed | 19:00:30 | 0 | -9 | -4320 | 180 | 10000 | 0 | 0 | 0.79201 | 13:59:30
4 | 1 | Product 1 | 2024-08-21 | 2024-08-20 | 9000 | C4 | Op4 | In House | M1 | 30 | 1.08 | 10000 | 2024-05-23 09:00 | 2024-08-23 11:33 | 2024-08-23 16:03 | 02:33:00 | Late | 04:30:00 | 0 | -17 | -8160 | 270 | 10000 | 3 | 7 | 0.1875 | 04:30:00
5 | 1 | Product 1 | 2024-08-21 | 2024-08-20 | 9000 | C5 | Op5 | In House | M3 | 15 | 7.2 | 10000 | 2024-05-23 09:00 | 2024-08-23 16:04 | 2024-08-26 10:19 | 07:03:30 | Late | 18:15:30 | 0 | -17 | -8160 | 135 | 10000 | 6 | 1 | 2.7608 | 14:44:30
6 | 1 | Product 1 | 2024-08-21 | 2024-08-20 | 9000 | C6 | Op5 | In House | M3 | 14 | 7.2 | 10000 | 2024-05-23 09:00 | 2024-08-26 10:20 | 2024-08-26 12:26 | 01:19:30 | Late | 02:06:00 | 0 | -17 | -8160 | 126 | 10000 | 6 | 3 | 0.0875 | 06:54:00
7 | 2 | Product 2 | 2024-08-19 | 2024-08-27 | 4000 | C1 | Op1 | In House | M1 | 30 | 3 | 0 | 2024-05-23 09:00 | 2024-08-19 16:32 | 2024-08-20 10:32 | 07:32:00 | Completed | 18:00:00 | 0 | -10 | -4800 | 120 | 0 | 0 | 0 | 0.75 | 15:00:00
8 | 2 | Product 2 | 2024-08-19 | 2024-08-27 | 4000 | C2 | Op2 | In House | M2 | 30 | 7.2 | 10000 | 2024-05-23 09:00 | 2024-08-20 10:32 | 2024-08-20 12:33 | 01:32:30 | Completed | 02:00:00 | 0 | -10 | -4800 | 120 | 10000 | 0 | 0 | 0.083333 | 07:00:00
9 | 2 | Product 2 | 2024-08-19 | 2024-08-27 | 4000 | C3 | Op3 | Outsource | OutSrc | 700 |  | 0 | 2024-05-23 09:00 | 2024-08-20 12:33 | 2024-08-26 12:26 |  | Completed | 23:52:30 | 1 | -10 | -4800 | 700 |  |  |  | 5.9948 | 09:07:30
10 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C1 | Op1 | Outsource | OutSrc | 1440 |  | 10000 | 2024-05-23 09:00 | 2024-08-20 12:33 | 2024-08-27 09:52 |  | Completed | 21:19:00 | 1 | -4 | -1920 | 1440 |  |  |  | 6.8882 | 11:41:00
11 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C2 | Op2 | In House | M1 | 30 | 1.08 | 10000 | 2024-05-23 09:00 | 2024-08-27 09:53 | 2024-08-28 09:23 | 00:52:30 | Completed | 23:30:30 | 0 | -4 | -1920 | 450 | 10000 | 0 | 0 | 0.97951 | 09:29:30
12 | 3 | Product 3 | 2024-08-21 | 2024-09-02 | 15000 | C3 | Op3 | In House | M2 | 40 | 7.2 | 10000 | 2024-05-23 09:00 | 2024-08-28 09:24 | 2024-08-29 11:24 | 00:23:30 | Completed | 02:00:30 | 0 | -4 | -1920 | 600 | 10000 | 0 | 0 | 1.0837 | 06:59:30
13 | 4 | Product 4 | 2024-08-21 | 2024-08-29 | 5000 | C1 | Op1 | Outsource | OutSrc | 750 | 1.08 | 10000 | 2024-05-23 09:00 | 2024-08-20 12:33 | 2024-08-26 12:26 |  | Completed | 23:52:30 | 1 | -8 | -3840 | 750 |  |  |  | 5.9948 | 09:07:30
14 | 4 | Product 4 | 2024-08-21 | 2024-08-29 | 5000 | C2 | Op2 | In House | M1 | 35 |  | 10000 | 2024-05-23 09:00 | 2024-08-26 12:26 | 2024-08-26 15:21 | 03:26:00 | Late | 02:55:00 | 0 | -8 | -3840 | 175 | 10000 | 0 | 0 | 0.12153 | 06:05:00
15 | 4 | Product 4 | 2024-08-21 | 2024-08-29 | 5000 | C3 | Op3 | In House | M2 | 30 | 7.2 | 10000 | 2024-05-23 09:00 | 2024-08-26 15:22 | 2024-08-27 09:52 | 06:21:30 | Completed | 18:30:30 | 0 | -8 | -3840 | 150 | 10000 | 0 | 0 | 0.77118 | 14:29:30
16 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C1 | Op1 | In House | M1 | 40 | 1.08 | 10000 | 2024-05-23 09:00 | 2024-08-20 12:33 | 2024-08-20 14:33 | 03:33:00 | Completed | 02:00:00 | 0 | -7 | -3360 | 120 | 10000 | 0 | 0 | 0.083333 | 07:00:00
17 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C2 | Op2 | In House | M2 | 40 | 7.2 | 10000 | 2024-05-23 09:00 | 2024-08-20 14:34 | 2024-08-20 16:34 | 05:33:30 | Completed | 02:00:00 | 0 | -7 | -3360 | 120 | 10000 | 0 | 0 | 0.083333 | 07:00:00
18 | 5 | Product 5 | 2024-08-21 | 2024-08-30 | 3000 | C3 | Op3 | In House | M2 | 35 | 7.2 | 10000 | 2024-05-23 09:00 | 2024-08-20 16:34 | 2024-08-21 10:19 | 07:34:00 | Completed | 17:45:00 | 0 | -7 | -3360 | 105 | 10000 | 0 | 0 | 0.73958 | 15:15:00
20 | 6 | Product 6 | 2024-08-21 | 2024-08-19 | 4000 | C1 | Op1 | In House | M1 | 30 | 7.2 | 10000 | 2024-05-23 09:00 | 2024-08-19 09:00 | 2024-08-19 11:00 | 00:00:00 | Late | 02:00:00 | 0 | -18 | -8640 | 120 | 10000 | 0 | 2 | 0.083333 | 07:00:00
21 | 6 | Product 6 | 2024-08-21 | 2024-08-19 | 4000 | C2 | Op2 | In House | M2 | 30 |  | 10000 | 2024-05-23 09:00 | 2024-08-19 11:01 | 2024-08-19 13:00 | 02:00:30 | Late | 02:00:00 | 0 | -18 | -8640 | 120 | 10000 | 0 | 4 | 0.083333 | 07:00:00
22 | 6 | Product 6 | 2024-08-21 | 2024-08-19 | 4000 | C3 | Op3 | In House | M3 | 30 | 1.08 | 10000 | 2024-05-23 09:00 | 2024-08-19 13:01 | 2024-08-19 15:01 | 04:01:00 | Late | 02:00:00 | 0 | -18 | -8640 | 120 | 10000 | 0 | 6 | 0.083333 | 07:00:00

## Product Times
Product Name | Total Time | Remaining Time | Time_Needed | Time Left | Date
Product 6 | 360 | 360 | -8640 | -9000 | 09-09-2024
Product 1 | 2241 | 531 | -6240 | -6771 | 10-09-2024
Product 2 | 940 | 700 | -4800 | -5500 | 10-09-2024
Product 4 | 1075 | 1075 | -3840 | -4915 | 11-09-2024
Product 3 | 2490 | 2490 | -1920 | -4410 | 16-09-2024
Product 5 | 345 | 0 | -3360 | -3360 | 06-09-2024

## Addln
UniqueID | Sr. No | Product Name | Order Processing Date | Promised Delivery Date | Quantity Required | Components | Operation | Process Type | Machine Number | Run Time (min/1000) | Cycle Time (seconds) | Setup time (seconds) | Ready Time | Start Time | End Time | Wait Time | Status | Time Diff

## RunTime
Run_time
12

## Outsource Time
Product | Components | Outsource Time
Product 1 | C2 | 5
Product 2 | C3 | 5
Product 3 | C1 | 5

## Machines
Machines
M1
M2
M3

## Similarity
Machine | Product 1 | Product 2 | Product 3 | Product 4 | Product 5 | Product 6
M1 | 0 | 0 | 0 | 0 | 0 | 0
M2 | 0 | 0 | 0 | 0 | 0 | 0
M3 | 0 | 0 | 0 | 0 | 0 | 0